“Predictability”

Project: ALADIN-LAEF

Principle Investigator: Yong Wang (YW)

Scientist: Florian Weidle (FW), Martin Bellus (MB), Mate Mile (MM),

Mirela Niculae (MN),  Olda Spaniel (ASC), Simona Tascu (ST),

Lorvo Kalin (LK), Stjepan Ivatek-Sahdan (SI), Geert Smet (GS)

Scientist left: Alexander Kann (AK), Martin Steinheimer (MS), Richard Mladek (RM), Raluca Radu (RR)

Task 1:  LAEF Research

D1:  Clustering of ECMWF EPS members

D2:  Initial condition perturbation-Blending

D3:  Initial surface condition perturbation-NCB/B

D4:  Multi-physics in LAEF

D5:  Combination of LAEF/ECMWF EPS and LAEF/PEARP

D6:  International projects such as MAP D-Phase, EurEPS, GLAMEPS

D7:  Publication of the scientific results archived within the project

# Task 2:  Verification and Calibration

- D8:  EPS verification package

- D9:  Statistical Calibration and post-processing

Task 3:  Application (Implementation and optimization)

D10:  Upgrading LAEF forecast at LACE WEB page

D11:  LAEF SMS setting at ECMWF for Time Critical Application II

D12:  Technical Optimization of LAEF on ECMWF HPCE

D13:  LAEF post-processing domain cover Black-Sea (Romanian requirement)

| Tasks | Deliverable | Total | AU |  | CZ | HR | HU | RO | SI | SK | Non LACE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task 1 | D1 2008 |  | 2 NN, YW |  |  |  |  |  |  |  |  |
|  | D2 2008 |  | 1 AK, YW |  |  |  |  |  |  | 1.5 MB |  |
|  | D3 2008 |  | 1 MS, YW |  |  |  |  |  |  |  |  |
|  | D4 2008 |  | 1 CW, YW |  |  |  |  |  |  |  |  |
|  | D5 2008 |  | 0.5 FW, YW |  |  |  |  | 1 ST |  |  |  |
|  | D6 2008 |  | 3 AK, MS, CW, YW |  |  |  |  |  |  |  |  |
|  | D7 2008 |  | 2.5 AK, MS, CW, YW |  |  |  |  |  |  | 0.5 MB |  |
| Task 2 | D8 2008 |  |  |  |  |  |  |  |  |  |  |
|  | D9 2008 |  | 2 AK, YW |  |  | 1 LK |  |  |  |  |  |
| Task 3 | D10 2008 |  |  |  |  |  |  |  |  |  |  |
|  | D11 2008 |  |  |  |  |  |  |  |  |  |  |
|  | D12 2008 |  |  |  |  |  |  |  |  |  |  |
|  | D13 2008 |  |  |  |  |  |  |  |  |  |  |
| Total | 17 |  | 13 |  | 0 | 1 | 0 | 1 | 0 | 2 |  |
| LACE funds |  |  | 1 |  |  | 1 |  | 1 |  | 1.5 |  |

2008

| Tasks | Deliverable | Total | AU | CZ | HR | HU | RO | SI | SK | Non LACE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task 1 | D1 2009 | 1 | 1 FW, YW |  |  |  |  |  |  |  |
|  | D2 2009/10 | 2.5 | 0.5 FW, YW |  |  |  |  |  | 2 MB |  |
|  | D3 2009/10 | 0 / 2 |  |  |  |  |  |  |  | 0 / 2 GS |
|  | D4 2009/10 |  |  |  |  |  |  |  |  |  |
|  | D5 2009/10 | 2.5 | 0.5 YW |  |  |  | 2 ST |  |  |  |
|  | D6 2009/10 | 1.5 / 3.5 | 1 FW, YW |  | 0.5 SI | 0 / 1 MM |  |  | 0 / 1 MB |  |
|  | D7 2009/10 | 4 | 2 FW, YW |  |  |  | 1 ST |  | 1 MB |  |
| Task 2 | D8 2009/10 | 0.5 | 0.5 FW |  |  |  |  |  |  |  |
|  | D9 2009/10 | 1 |  |  | 1 LK |  |  |  |  |  |
| Task 3 | D10 2009/10 | 1 | 0.5 FW |  |  |  |  |  | 0.5 ASC |  |
|  | D11 2009 | 3 | 3 FW |  |  |  |  |  |  |  |
|  | D12 2009 | 2 | 2 FW |  |  |  |  |  |  |  |
|  | D13 2009 | 2 | 1 FW, YW |  |  |  | 1 ST, MN |  |  |  |
| Total |  | 21 / 25 | 12 | 0 | 1.5 | 0 / 1 | 4 | 0 | 3.5 / 4.5 | 0 / 2 |
| LACE funds |  | 6 / 8 | 1 |  | 1 | 0 / 1 | 2 |  | 2 / 3 |  |

2009:  status Oct. 08 / Feb. 09 (in green)

2010

| Tasks | Deliverable | AU | CZ | HR | HU | RO | SI | SK | Non LACE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task 1 |  |  |  |  |  |  |  |  |  |
|  | D2 2010 | 0.5 FW, YW |  |  |  |  |  | 2 MB |  |
|  | D3 2010 | 2 FW, YW |  |  |  |  |  |  |  |
|  | D4 2010 | 2 FW, YW |  |  |  |  |  |  |  |
|  | D5 2010 | 0.5 YW |  |  |  | 2 ST |  |  |  |
|  | D6 2010 | 1 FW, YW |  | 0.5 SI |  |  |  |  |  |
|  | D7 2010 | 2 FW, YW |  | 1 LK |  | 1 ST |  |  |  |
| Task 2 | D8 2010 | 0.5 FW |  |  |  |  |  |  |  |
|  | D9 2010 |  |  | 1 LK |  |  |  |  |  |
| Task 3 | D10 2010 | 0.5 FW |  |  |  |  |  | 0.5 ASC |  |
| Total | 17 | 9 | 0 | 2.5 | 0 | 3 | 0 | 2.5 |  |
| LACE |  | 1 |  | 1 |  | 2 |  | 2 |  |