RC LACE Report on data assimilation:

2010

Gergely Bölöni

07 February, 2011

Content

1. Introduction									     1

2. Project report									     1

2.1 Relevant deliverables							     1

2.2 Status summary 							     2

2.3 Corresponding tasks 							     3

3. Long-term research topics						     	     7

4. Summary of means								   11

# 1. Introduction

According to the new planning practice of LACE, the work has been structured in two different classes. On the one hand a project was prepared with a strict definition of operational deliverables and a clear specification of needed resources on a 2-3 year time scale. On the other hand long-term research topics were described, which were not in the state of delivering operational benefits during the next 2-3 years but rather on the 3-5 year time scale. This report also consists of two parts. The first part describes the achievements in the frame of the projects (operational deliverables), the second part describes the progress in the long term research topics.

# 2. Project report

# Project name: Development of an operational data assimilation system for LACE

Responsible person: Gergely Bölöni

Responsible Center: HMS

2.1 Relevant deliverables

Figure 1 shows the schedule of deliverables in the project (taken from the project plan). This reflects that the relevant deliverables for the first half of 2010 are is D4. However work to complete deliverables D3, D6 and D7 has been done too during tha lat 6-7 months. Deliverable D9 is in a late due to somewhat unexpected scientific results.

Task 2

Jan 2008

Jan 2009

Jan 2010

Jan 2011

Task 1

D2

D3

D4

D5

D6

D7

Task 3

D8

D9

D10

Jul 2009

Jul 2010

D1

# Figure 1: Schedule of deliverables

2.2 Status summary

Deliverables of the project (those relevant for the first half of 2010):

D3: Upgraded preprocessing software at HMS with optimized data formats (end of 2009). This work has been continued during 2010. Two main aspects of OPLACE were improved during 2010/1.

- ATOVS and GEOWIND data are operationally disseminated in BUFR format (beside the earlier OBSOUL format) since 19 May 2010. This makes possible the use of 2 new satellites: NOAA-19 (AMSU-A and AMSU-B) and METOP (AMSU-A and AMSU-B).

- OPALCE was migrated (mirrored) to a server of the IT group of HMS in order to increase the reliability. This can be run in an operational framework but the input data sources are not yet independent from the present operational OPLACE machine (so in case of shut down of the present system, still not all data can be processed and sent to OPLACE from the mirror system). Here we depend on the data organization work of the IT team.

D4: Local monitoring reports in LACE centers (mid. 2010). The observation monitoring software is installed and regularly used in AU, CZ, CR, HU and SI. The installation is ongoing in RO.

D6: Reports on installation and validation of 3DVAR (upper air) and CANARI OI (surface) analysis systems in LACE centers (end of 2008). AU, CZ, HR and SI completed the installation and basic validation of the data assimilation related model configurations (screening, 3DVAR minimization, surface OI assimilation) in 2009. They were also setting up data assimilation suites and doing comparisons. During 2010 the validation of all the data assimilation configurations took place in RO with the help of AL. SK validated the OI surface assimilation. Table 1. shows the status of the installations.

D7: Reports on the operational use of 3DVAR (upper air) and CANARI (surface) analysis systems in LACE centers including comparison with the former operational model (end of 2009). So far no new operational implementation is done in any of the LACE countries. (Blending is operational in SK, Blending + CANARI is operational in CZ and 3DVAR + CANARI is operational in HU). Parallel tests and tuning experiments continuously take place in AU, CZ, HR, SI but so far no overall improvement was confirmed compared to the present operational runs. HR reported rather good results, which in terms of scores beat the dynamical adaptation run. It is expected that most of the countries will achieve an operational setup only in 2010 or 2011.

D9: Report on the comparison of FGAT/RUC system with the operational assimilation system at HMS (end of 2009). This work was pending during 2010. The last parallel test (2009) with 3-h cycling (RUC) in the operational environment did not show an improvement compared to the operational (6h cycling) results. This is not inline with earlier results. One possible reason for it, is the interaction of the Variational Bias Correction (VARBC) and the 3h cycling (earlier RUC tests were always done with static bias correction of satellite data) but it has to be still tested out.

|  | Software to treat observations | Quality control (screening) for atmospheric assimilation | Surface assimilation (Optimum interpolation) | Atmospheric assimilation (3DVAR) |
| --- | --- | --- | --- | --- |
| AU | OK | OK | OK | OK |
| CR | OK | OK | OK | OK |
| CZ | OK | OK | OK | OK |
| HU | OK | OK | OK | OK |
| RO | OK | OK | OK | OK |
| SK | OK | - | OK | - |
| SI | OK | OK | OK | OK |

# Table 1: Status related to deliverable D6. Green color indicates that the work is fulfilled, red color shows that no progress was done.

2.3 Corresponding tasks

# This section contains the description of the detailed work done related to the actual deliverables described in the previous section. The corresponding working tasks scheduled for of 2009 are listed in Table 2 (these tasks were defined in the reference LACE project plan for 2008-2010:

# http://www.rclace.eu/File/Data_Assimilation/plans/wp_da_2008_2010.7.doc).

| Task | Needed subtasks |
| --- | --- |
| Task 1 | T1.4, T1.5, T1.6 |
| Task 2 | T2.3, T2.4 |
| Task 3 | T3.1, T3.2 |

# Table 2: Tasks corresponding in 2010

#### T1.4: Upgrade the preprocessing system at HMS: include new observation types, optimization of data formats

Description: It is expected that during late 2008 and 2009 new observation types will come up to be included into the preprocessing system (i.e. METOP, radar winds). Also we should count with further changes in the data flow (having only BUFR and GRIB formats as an input for BATOR). These points will require some continuous work during 2009.

Realization:

- Direct reading of BUFR ATOVS (NOAA and METOP) and AMV (MSG) data has been tested by DM and Hungarian staff. Also a tool to merge and split tools by time-slots has been developed by DM, which is essential for distribution through OPLACE. ATOVS and AMV data are operationally distributed on OPLACE since 19 May 2010. Till the end of  September 2010 ATOVS and AMV data will be still distributed also in the old OBSOUL format. Note that this technical development makes possible to use to more satellites, NOAA-19 and METOP.

- OPLACE has been migrated (mirrored) to another server that will work as the primary system, while the present application (on the HMS SGI supercomputer) will serve as backup. The actual change of the new server as the primary one did not take place yet because some of the input observations (SEVIRI) are mounted there through SGI (which means that a possible shut down of SGI would still prevent the processing of some of the observation types).

Documentation: Forum (http://www.rclace.eu/forum/viewtopic.php?f=37&t=211)

Resources: 1.5 p.m

Staff: Gergely Bölöni (1 pm), Laszlo Szabo (0.5 p.m)

Schedule: 2010/1

### T1.5: Move to local observation monitoring at each center

Description: The ultimate goal is to have a decentralized observation monitoring in order to enable local bias corrections and true statistics of QC status of observations in the local assimilations. This requires the local installation of the monitoring software already developed at HMS in all LACE centers. It is expected that the installation can be managed by an English documentation and through the email help of HMS.

Realization: This task is scheduled to 2010 in the project, however some of the members (AU, CZ, HR, SI) completed the installation already in 2009. SK did the installation in2010.

Documentation: no

Resources: 0.25 p.m

Staff: Michal Nestiak (0.25 p.m)

Schedule: 2010/1

#### T1.6: Extend the centralized preprocessing and monitoring for national data

Description: It requires a common organization work of AL and DM to initiate the exchange of national data (mostly radars and SYNOPs will be useful for data assimilation) among LACE or even ALADIN and HIRLAM countries. This gets an increasing priority as going to finer scales with the assimilation system.

Realization: So far the following steps have been taken to improve the SYNOP availability in OPLACE:

- It has been agreed with OMSZ that the full set of Hungarian local SYNOP data can be distributed through OPLACE to LACE countries.

- A bug was fixed in the GTS SYNOP aggregation at the IT department of HMS, which completed the available GTS data with those of Croatia (earlier these data were missing from OPLACE).

- New format (more complete) SYNOP files are distributed though OPLACE adding about 200 more stations (per analysis time) compared to the previous SYNOP data. The additional data consist of previously nontreated GTS data but also of all Hungarian (and maybe other) national data. Additional data come mostly from  Hungary, Austria, Germany, and Switzerland, but also from Czech Rep., Bulgarian, UK and France.

- DM sent out a questionnaire to all LACE members to investigate the potential in national SYNOP data.

Documentation: no

Resources: 1.5 p.m

Staff: Gergely Bölöni (1 p.m), Laszlo Kullmann (0.5 p.m.)

Schedule: 2010/1

#### T2.1: Computation of background errors on local domains

Description: The computation of background errors requires a set of forecast differences created with one of the sampling methods (NMC, lagged-NMC or Ensemble method) according to the local preferences. These forecast differences are the inputs for the software for the computation of the background error covariance matrix, which should be installed and validated in each center.

Realization: An Ensemble B was computed based on the downscaling of the ARPEGE EnVar assimilation ensemble system. Unfortunately, as the RO coupling domain is different fromthe others in LACE, the pre-prepared LBC files from EnVar for this purpose could not be used. This means that RO colleagues had to run additional e927 to interpolate the EnVar files to their coupling domain. Based on the downscaled forecast differences a B matrix was computed based on the package prepared on the LACE forum.

Documentation: no

Resources: 1.25 p.m

Staff:  Mirela Niculae (1.25 p.m)

Schedule: 2010/1

##### T2.2: Installation and validation of needed model configurations for data assimilation

Description: As the input observations are required in ODB format in the ALADIN software, a tool for data conversion is to be installed and validated (BATOR). The inputs for BATOR are created and disseminated through the centralized preprocessing system described in Task 1. The BATOR program is part of the ALADIN software and beside data conversion it performs blacklisting and setting up of observation errors. Atmospheric and surface data assimilation in ALADIN requires the installation and validation of 3 further model configurations: conf. 002 (QC of observations for variational analysis), conf. 131 (variational analysis) and conf. 701 (optimum interpolation for the surface).

Realization: During the stay of AL in Bucarest, the three configurations (002, 131 and 701) and BATOR have been validated. The necessary binaries were already pre-compiled but missing some necessary compilation flags, so a new main pack was created for assimilation. The shell scripts from HU were adaped to run an assimilation cycling. The use OPLACE was tested including the use of satellite data in BUFR format. The cycling of microphysical fields is still missing fom the cycling script. In SK, conf. 701 was succesfully installed and validated. The installation work started for conf. 002 and 131 too.

Documentation: no

Resources: 4.5 p.m

Staff: Gergely Bölöni (0.25 p.m), Mirela Niculae (0.25 p.m), Cornel Soci, Michal Nestiak (4 p.m)

Schedule: 2010/1,2

#### T2.3: Evaluation of the assimilation system and preparation of an operational setup

Description: For running an assimilation cycle on a regular basis, a script system should be created. In countries already running a blending cycle, a complement with the data assimilation configurations is needed. Objective and subjective comparisons of the data assimilation suite with the actual operational model should be the basis for making a choice for the best setup for assimilation (blending, use of observations, use of background errors).

Realization: A lot of progress was done in setting up the operational data assimilation environments.

- AU) A bug was fixed in the coupling of the surface and atmospheric assimilation (correct mixing of the 3DVAR and CANARI analyses). Last experiments show that data assimilation (surface CANARI + 3DVAR) has a clear positive impact on the screen level parameters and also on 850 hPa for wind and temperature. Upper air scores could not be improved. Many tests were done to gradually switch off certain observation types, which show that radiosoundings have clear positive impact, satellites rather small positive impact and synops surprisingly negative impact. This was partly coming from the effect of mountainous stations where the model orography is far from the real one. The impact was somewhat better after preparing a blacklist for synop stations with large height differences compared to the model orography. In the CANARI part also a snow analysis is performed. This produces too much snow compared to reality (and also Arpege), which leads to cold biases in winter.

- CZ) According to the results in 2009 the atmospheric 3DVAR improves the forecasts only in the first 12 hours compared to the Blending + CANARI suite. The impact of AMDAR data was studied still in 2009 showing an improvement over the use SYNOP+TEMP data only. VARBC was implemented and during 2010 compared to the static satellite bias correction method, with the conclusion that VARBC slightly improves (reduces more) biases compared to the static bias correction.

- HR) An Ensemble B matrix was computed (downscaled from the ARPEGE EnVar system) and diagnosed in comparison with the regularly used standard NMC background error covariance matrix. Verification against radiosondes and surface stations show an improvement by the assimilation in spring 2010. However during the summer months (June, July) the improvement by assimilation slowly disappears at 2m and turns into a slight degradation, with a wet bias.

- HU) The use of VARBC was improved by replacing the 6h cycling of the bias coefficients by a daily cycling separately for the 4 network times (00, 06, 12, 18 UTC). Technical developments were done to read all satellites in BUFR format (available on OPLACE since mid-May 2010). The assimilation of a more complete  SYNOP data file (about 200 more stations mostly from Hungary, Austria and Germany) was tested with rather slight positive impact on the forecasts.

- SI) DA is run on 4.4 km resolution. Recent results show no improvement compared to the corresponding dynamical adaptation run. Partly it may come from the fact that 2m T and RH was not used accidentally in the recent times. The B matrix was recomputed on a large sample by downscaling the ARPEGE EnVar ensemble DA system outputs (June 2007). VARBC is under evaluation. The "X-pattern" bugfix in the xrd/fa routines cured an error, which happened randomly in the cycling.

Documentation: The detailed reports are available on the LACE website.

Resources:  11.5 p.m

Staff: Antonio Stanesic (3 p.m), Patrik Benacek (3 p.m), Florian Meier (3 p.m), Benedikt Strajnar (1 p.m), Gergely Boloni (1 p.m), Laszlo Kullmann (0.5 p.m)

Schedule: 2010/1

#### T2.4: Maintenance of the data assimilation system: update with new observation types and follow research and developments

Description: A data assimilation system requires scientific maintenance even after its operational implementation, which targets a continuous update of the system with newly applicable observation types and with novelties coming from the research and development. Implicitly, this includes the installation and validation of new cycles of the ALADIN software similarly to T2.2.

Realization: CZ migrated the assimilation system to the new operational machine (SX9) and started to port CY36, Hungary went to CY35T1 (in parallel suite) from CY33T1 and started the migration to the new IBM.

Documentation: The reports for T2.3 include these details as well (available on the LACE website).

Resources: 6.5 p.m

Staff: Gergely Bölöni (0.5 p.m), László Kullmann (1 p.m), Mate Mile (1 p.m), Antonio Stanesic (1 p.m), Alena Trojáková (2 p.m), Jure Cedilnik (0.5 p.m), Benedikt Strajnar (0.5 p.m)

Schedule: 2010/1

T3.2: Evaluation of the FGAT/RUC assimilation in comparison with the actual operational assimilation at HMS on a regular basis

Description: If T3.1 is successful, FGAT and RUC should be implemented and run on a regular basis at HMS first enabling a continuous comparison with the actually operational 6-hourly 3DVAR suite. This will require some upgrade of the preprocessing tools and cycling scripts from technical point of view and additionally a detailed verification of results and monitoring of the observation use.

Realization: The RUC 3-h cycling has been put in a parallel suite in the operational environment of HU for a 4 weeks period (03-27.12.2009). Verification against ECMWF analysis already shows that there is a degradation in the humidity scores (other variables are slightly improved). Verification against observations is being prepared. One possible source for the unexpected degradation is the use of VARBC in 3h cycling but it has to be tested out (earlier RUC tests were always done with static bias correction of satellite data).

Resources: 0 p.m

Staff: Gergely Bölöni (0 p.m), Edit Adamcsek (0 p.m)

Schedule: 2010/1

# 3. Long-term research topics

Topic 1: Development of ALADIN 4DVAR

Description: The development of ALADIN 4DVAR for meso-scales is very important for the long-term. LACE will contribute most probably to the design of a first version ALADIN 4DVAR prototype and to the improvement of the simplified (tangent-linear and adjoint) physics. An intensive cooperation is foreseen here with Meteo-France and HIRLAM.

Realization: No work in 2010 yet.

Documentation:

Resources: 0 p.m

Staff:

Schedule:

Topic 2: Research on background error modeling

Description: On one hand the research will focus on the time variability (or flow dependency) of background errors. This will be tackled mostly by the development of an ETKF (Ensemble Transform Kalman Filter) system, which enables to evolve the background error covariance matrix in time. It would be beneficial to compare ETKF with EnsVar (Ensemble Variational Assimilation), which is the strategy chosen at Meteo France. Beside the time variability, the spatial variability of background errors will also be in the scope of this research. A member of the Slovenian team started already a work on the grid-point representation of background error variances (instead of the presently used spectral representation), which will presumably continue. A close cooperation with Meteo France is expected on both issues.

Realization:

CZ) The tools for B matrix computation were validated on the new SX9 computer of CHMI.

HU) 1) The first results with ETKF were published. 2) A 5 member local LAM ensemble assimilation experiment was run using the ECMWF EDA system for LBC over the Hungarian operational model domain. This system was used then to sample background errors. The point was to investigate what is the information added by taking into account local initial uncertainties compared to the case when the sampling is done from the downscaled EDA system. Diagnostics show an increased variance on small scales and a better representation of background errors in the case of including the LAM perturbations.

SI) 1)A diagnostic comparison of downscaled ensemble B statistics was done based on the Arpege EnVar system an the ECMWF EDA system. There have been slight differences both in the variance spectra and the balance matrices between variables, however the real impact on the LAM analysis was not tested yet. 2) A study to estimate model error (Q matrix) of ALADIN and AROME was carried out in Toulouse. The estimation is based on the idea that the correction by the "a posteriori" diagnosis is mostly due to the lack of representing model error. Then if this correction is quantified, the ensemble for sampling might be inflated with it to represent model error (at least on the level of variances). The diagnosis was done on an AROME ensemble assimilation system and by two methods: a) the method of residual correlations in observation space and b) the Jmin method. The two methods in AROME gave relatively different corrections, though they were very similar in ARPEGE. This raises the question whether the two diagnostic methods are still applicable in a very high resolution model (2.5km resolution).

Documentation: available on the LACE website (for the SI work so far), an article is published in Idojaras for the ETKF work

Resources:  7.5 p.m

Staff: Gergely Bölöni (1.5 p.m), Edit Adamcsek (1.5 p.m), Benedikt Strajnar (3.5 p.m), Antonin Bucanek (1 p.m)

Schedule: February-August 2010

Topic 3: Research on surface assimilation

Description: With the leadership of Meteo France, a surface assimilation scheme is being developed based on a simplified Extended Kalman Filter. This scheme will be incorporated into the externalized surface scheme (SURFEX) and will be capable for using also satellite-based inputs on the top of 2m observations. LACE will contribute to the work through preparation of specific inputs for EKF combining Land SAF (Satellite Application Facilities) and ECOCLIMAP data. A part of the work will also account for validation of NWP models using the same data. Another important component of this topic is to prepare for the technical switch to SURFEX, which is expected by the end of 2009 or during 2010. This switch will imply changes in the surface data assimilation even if the EKF assimilation will not be ready for operational use. Namely, a substitution of the present scheme coded under CANARI (conf. 701) will be needed. The reimplementation of the present surface analysis scheme is already being implemented in SURFEX to this end in Meteo France. Our aim is to get experience with the surface assimilation through SURFEX before the switch to SURFEX will happen.

Realization:

SI) The albedo assimilation from LANDSAF was found to be rather successful over a full year period, improving the screen level parameters. Consequently, a technical development was done to rewrite the corresponding code in a more modular way preparing it for an operational use. The assimilation of LANDSAF snow information was combined with the CANARI snow assimilation. This is done by correcting the first guess snow amount by those of the LANDSAF product (add where there is surely snow by LANDSAF but not in the model and remove where there is surely no snow in LANDSAF but there is in the model). Then the upgraded first guess is used by CANARI snow assimilation. The CANARI snow assimilation was upgraded mainly by 2 features: a) snow height is assimilated instead of snow water content (as before). This is more exact than the previous method as measurements are done for snow height which can be transferred to snow water content quantity only knowing the snow density (which is usually not measured). On the other hand in the model both the snow water content and the snow density is given, thus the snow height can be easily computed, which enables a direct comparison with the measured quantities. b) A trial to introduce weather dependent background errors in CANARI was done. An old option of the code was reused, which enables to write analysis errors to FA file. This analysis error can then be inflated and used in the next assimilation step as background error. The inflation tried consisted of adding the precipitation fluxes to the analysis error, which leads to less reliable background in areas where precipitation was falling in the model and thus giving a relatively large weight to the snow observations (if there are).

AU) Technical developments were done on the ASCAT assimilation code. The most important aspect is that CANARI is introduced as an intermediate step of the analysis for providing the 2m increments for the SURFEX soil analysis. Tests with ASCAT assimilation consisted of modifying the CANARI background errors to improve the input 2m increments, however with not many differences. The impact of ASCAT analysis is a cold and wet bias at 2m, which can lead to improvements during the night but rather to degradation during the day. SAL verification did not show a clear improvement of precipitation forecasts while ASCAT data are used.

Documentation: A detailed report on the LANDSAF albedo and snow assimilation are included to the status report of SI and the results with ASCAT assimilation are described in the status report of Austria (available on the LACE website).

Resources: 6.5 p.m

Staff: Jure Cedilnik (3.5 p.m), Stefan Schneider (3 p.m)

Schedule: Jan-June 2010

Topic 4: Research on radar reflectivity assimilation

Description: Meteo France is developing a facility for the assimilation of radar reflectivities in the ALADIN variational analysis. LACE is contributing to this research through the development of the quality control. In 2010 a new work plan was set up in LACE to start feeding ODB with CE radar data and also to adapt the reflectivity operator (developed for AROME) to ALARO microphysics.

Realization: The reading of Croatian radar is successfully prepared inside the CONRAD framework (a Norwegian package based on the preprocessing tool prepared at Meteo-France). It is an ongoing work to feed ODB with these data. Also a visualization tool was written for radar data.

Documentation: No

Resources: 4 p.m

Staff: Tomislav Kovacic (4 p.m)

Schedule: Jan-June 2010

# Topic 5: GPS assimilation

Decription: The aim is to use GPS ZTD (Zenith Delay) data in the ALADIN 3DVAR system. The work will account for the preprocessing of the data and for running impact studies using them. Austrian high-resolution GPS data are considered in the assimilation experiments

Realization: Impact studies included 2 main GPS networks: the E-GVAP (GPS network monitored by EUMETNET) and a high density Austrian network. Experiments with both networks show a bigger impact. The impact is mostly positive on forecasts of rainy periods and rather mixed in dry situations. SAL verification shows a trend of better locations, mean and standard deviations.

Dosumentation: included in the AU national report (available on the LACE web)

Resources: 3 p.m

Staff: Xin Yan (3 p.m)

Schedule: Jan-June 2010

4. Summary of means

|  | T1.4 | T1.5 | T1.6 | T2.1 | T2.2 | T2.3 | T2.4 | T3.2 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Florian Meier |  |  |  |  |  | 3 |  |  | 3 |
| Alena Trojakova |  |  |  |  |  |  | 2 |  | 2 |
| Patrik Benaček |  |  |  |  |  | 3 |  |  | 3 |
| Antonio Stanesic |  |  |  |  |  | 3 | 1 |  | 4 |
| Gergely Boloni | 1 |  | 1 |  | 0.25 | 1 | 0.5 |  | 3.75 |
| Laszlo Kullmann |  |  | 0.5 |  |  | 0.5 | 1 |  | 2 |
| Mate Mile |  |  |  |  |  |  | 1 |  | 1 |
| Laszlo Szabo | 0.5 |  |  |  |  |  |  |  | 0.5 |
| Mirela Niculae |  |  |  | 1.25 | 0.25 |  |  |  | 1.5 |
| Jure Cedilnik |  |  |  |  |  |  | 0.5 |  | 0.5 |
| Benedikt Strajnar |  |  |  |  |  | 1 | 0.5 |  | 1.5 |
| Michal Nestiak |  | 0.25 |  |  | 4 |  |  |  | 4.25 |
| Total | 1.5 | 0.25 | 1.5 | 1.25 | 4.5 | 11.5 | 6.5 | 0 | 27 |

# Table 4: Summary of manpower spent on the operational DA implementation project in 2010/1

|  | Topic1: 4DVAR | Topic2: B modeling | Topic3: Surcace | Topic4: Radar | Topic5: GPS | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Stefan Schneider |  |  | 3 |  |  | 3 |
| Xin Yan |  |  |  |  | 3 | 3 |
| Antonin Bucanek |  | 1 |  |  |  | 1 |
| Tomislav Kovacic |  |  |  | 4 |  | 4 |
| Edit Adamcsek |  | 1.5 |  |  |  | 1.5 |
| Gergely Boloni |  | 1.5 |  |  |  | 1.5 |
| Jure Cedilnik |  |  | 3.5 |  |  | 3.5 |
| Benedikt Strajnar |  | 3.5 |  |  |  | 3.5 |
| Total | 0 | 7.5 | 6.5 | 4 | 3 | 21 |

# Table 4: Summary of manpower spent on research topics in 2010/1