LACE Research and Development on Predictability

Working Group Report 2006

Yong Wang, Feb. 2007

Contents

- Introduction 									2

- Fulfilment of the research and development 					2

  - Dealing with uncertainties in initial condition				2

  - Dealing with uncertainties in lateral boundary conditions			3

  - Dealing with uncertainties in model physics				4

  - Dynamical downscaling of ECMWF EPS					5

  - EPS post-processing								5

  - Common EPS verification							5

  - Comparison between SRNWP-PEPS and ALADIN LAEF experiments	6

  - Dynamical downscaling of ARPEGE EPS					6

- International collaboration / participation on projects related with LAMEPS										6

- Other activities									7

- Summary of the means and status of the work in 2006			8

1.  Introduction

In 2006, the efforts for research and development on predictability in LACE have been focused on dealing with the uncertainties in analysis, in lateral boundary conditions, and in the model. Other issues related LAMEPS, like dynamical downscaling, post-processing and common verification have been also addressed. Large part of the plan for 2006 has been fulfilled. Due to some changes in the plan, some subjects have not been touched. In the following, the fulfilment of the plan for 2006 will be summarized after the same scheme as in the plan for 2006. Some detailed scientific results for part of the subjects can be found in the report from September 2006.

2.  Fulfillment  of the research and development plan for 2006

  - Dealing with uncertainties in initial condition

- Breeding

Description and objectives: The Breeding method for generation of analysis perturbations has been implemented, and some configurations of Breeding have been tested. More investigations are still needed, e.g. one side perturbation, multi-physics Breeding etc.

Realization: Vienna

Efforts: 3/6 months

Contributors: Wang, Kann, visiting scientist

Documentation: ALADIN newsletter 29

Efforts have been put on the testing rescaling factor and breeding cycles. A one-month test which makes the verification meaningful were carried out with 10 members Breeding. Due to limited computer capacity, experiments with one side perturbation and multi-physics perturbation haven’t done.

- Ensemble Transform Kalman Filter (ETKF)

Description and objectives: ETKF  has been implemented in LAEF for constructing the initial perturbation. The ETKF analysis perturbations are achieved by post-multiplying the short-term ensemble forecast perturbations by a transformation matrix. One-side forecast perturbation generation is applied. Since the ETKF analysis perturbation is not centred around the analysis, we applied a spherical simplex transformation for preserving the analysis error covariance and the perturbation is around the analysis. When the number of ensemble perturbations is much smaller than the number of directions to which the forecast error variance projects, the total analysis error variance will be significantly underestimated because of the lack of contribution from important parts of the error space. To ameliorate this problem, two methods for inflating the perturbation will be tested. The one is the innovation inflation technique; the other is a similar one as used in the Breeding.

Realization: Vienna

Efforts: 3 person x month

Contributors: Wang, visiting scientist, student

Documentation: not available yet

Same as Breeding, a one-month test for 10 members ETKF has been carried out. A preliminary comparison between ETKF with Breeding and ET has been done. The inflation method used in the experiment is the similar one used as in Breeding. The innovation inflation technique was not tested for this one-month test. Only some case studies were done with this innovation inflation technique.

- Ensemble Transform (ET)

Description and objectives: Like ETKF, the ET is also implemented in LAEF. This method is very similar to Breeding, but it uses the ensemble transform technique to make orthogonalization of the bred vector. Experiments will be done for verifying the performance of ET.

Realization: Vienna

Efforts: 3 person x month

Contributors: Wang, visiting scientist, student

Documentation: not available yet

Same as ETKF, a one-month test for 10 members ET has been carried out. A preliminary comparison between ET with Breeding and ETKF has been done.

- ALADIN Singular Vector (SV)

Description and objectives: The aim is to generate ALADIN native singular vector perturbations and to build LAMEPS runs on them. The work has already been started with  validation of the configuration 601 in the current cycle of ALADIN in HU. Later on, tests and validation of perturbations generated by ALADIN singular vectors will be carried out. Finally, an ALADIN EPS based on singular vectors will be built.

Realization: Budapest

Estimated efforts: 5 person x month

Proposed contributors: Hágel, Horanyi

Documentation: A short report is available by Horanyi

Research with ALADIN SV has been started in 2006 at Budapest. As a first step conf  401, 501 and finally 601 was used and tested. Speed of the convergence (during the singular vector computation), as  well as CPU time and memory usage was analyzed. These are quite important issues, since the number of iterations performed determines the accuracy of the computed singular values/vectors. The first results with the ALADIN singular vectors were presented in the ALADIN HIRLAM LAMEPS workshop in Vienna in November, 2006. More details is available from Hágel and Horanyi.

- Blending ARPEGE PEARP and ALADIN LAEF

Description and objectives: The idea is using ALADIN blending technique to combine the large-scale uncertainty from the ARPEGE PEARP with the small-scale uncertainty generated by Breeding/ET in ALADIN LAEF. It is expected that, 1). this can be reducing the inconsistency between the different perturbation method used in global ensemble system which determine the perturbation at the boundaries and the initial analysis perturbation method used in limited area ensemble prediction system, 2). small-scale uncertainty in analysis will be more detailed described, furthermore, 3). The future uncertainty generated by SV and the uncertainty in the history generated by Breeding are all presented in the analysis.

Realization: Vienna

Efforts: 3 person x month (1 month LACE Funding)

Contributors: Wang, Bellus, Kann

Documentation: stay report of Bellus, LACE web

The blending software for combining the large-scale uncertainty from the ARPEGE EPS with the small-scale uncertainty generated by Breeding in ALADIN has been implemented. The first results has been also achieved by a one-month test. More detail about this blending can be found in the report of Bellus (LACE web)

  - Dealing with uncertainties in lateral boundary conditions

- Impact of the inconsistent LBC perturbation with IC perturbation

Description and objectives: For investigating the impact of the inconsistency in the generation of ensemble lateral boundary conditions from global EPS system with the generation of the ensemble initial conditions from the limited area ensemble system itself, it is planned to do experiments of ALADIN LAEF with perturbations of lateral boundary conditions from different global ensemble systems NCEP (with Breeding) and ARPEGE (with singular vector) superimposed on control lateral boundary conditions, e.g. from ARPEGE,  the method of the initial conditions perturbation will be Breeding or ET.

Realization: Vienna

Efforts: 3 person x month

Contributors: Kann, Wang, visiting scientist

Documentation: ALADIN newsletter 31

Experiment has been made for a one-month test with ALADIN Breeding coupled with ARPEGE EPS (SV) and with NCEP EPS (Breeding). The aim is to investigate the impact of the mismatch between the perturbation generation methods for initial condition and the one of global EPS system, very preliminary verification was carried out.

  - Dealing with uncertainties in model physics

- Multi-physics option

Description and objectives: ALADIN dynamical downscaling of ARPEGE PEARP members with and without multi-physics options. 11 combinations of different physics parameterizations and tunings in ALADIN have been chosen for dealing with the uncertainty in the model physics,  they are: Bougeault-type scheme of deep convection, the modified Kain-Fritsch deep convection scheme, moisture convergence and CAPE closure in the convection scheme, Kessler-type scheme for large scale precipitation, Lopez microphysics scheme, tuning of the mixing length, entrainment rate, and the computation of the cloud base. Experiments will be done for a one-month period and case study.

Realization: Vienna

Efforts: 2 person x month

Contributors: Wang, Kann, Wittmann

Documentation: ALADIN newsletter 30

Experiment has been made for a one-month test with using 11 combinations of different physics parameterizations and tunings in ALADIN. The result was used to compare with the simple dynamical downscaling of ARPEGE EPS.

- Stochastic physics / Stochastic Kinetic Energy Backscatter Algorithm

Description and objectives: To account for the uncertainty in the model more consistently, in particular, in the model physics, it is considered that the stochastic physics scheme (ECMWF) or the stochastic kinetic energy backscatter algorithm SKEB (UKMO, ECMWF) will be implemented. Contacts with ECMWF and UKMO have been established.

Realization: Vienna

Efforts: 3 person x month (1.5 month LACE Funding)

Contributors: Wang, Tascu, Wittmann

Documentation: not available

This subject was not touched because of the change of research focus. The 1.5 month funding proposed  was shifted to the subject of ALADIN dynamical downscaling of ECMWF EPS.

  - Dynamical downscaling of ECMWF EPS

Description and objectives: The computational framework for dynamical downscaling the ECMWF EPS members with ALADIN will be implemented. Similar as COSMO-LEPS, the representative members of the ECMWF EPS are chosen by clustering, which are used as initial and lateral boundary conditions for ALADIN LAEF runs. Some interesting case studies will be investigated. Coordination with the ALADIN ECMWF special project (Fischer, Kertesz) for technical works at ECMWF is needed.

Realization: Zagreb, Vienna, Budapest

Efforts: 14.5 / 3  person x month, 2 months LACE funding

Contributors: Ivatek-Sahdan, Brankovic, Matjacic, Wang, Kertsez, Tascu, Pistotnik, Szintai and Ihasz

Documentation: stay reports of Pistotnik and Tascu, LACE web, ECMWF Tech. Memo.507, and papers by Horanyi.

This was one of the main subject in the last months in 2006. Manpower was put on to set up the computational framework of ALADIN downscaling of ECMWF EPS at ECMWF. With help of DM (Kertesz), some procedures have been implemented at ECMWF. In Zagreb, methods of clustering for having the representative members of ECMWF EPS have been investigated. In Budapest, case studies for dynamical downscaling of ECMWF EPS were carried out. More detail are available from Horanyi and Ivatek-Sahdan.

  - EPS post-processing

Description and objectives: The task is to develop a statistical post-processing scheme to reduce biases in ensemble forecasts (temperature, height, etc.). Both 1st and 2nd moments of the ensemble should be corrected. The bias-corrected forecasts will then have reduced or even no bias with respect to the verifying analysis fields.

Realization: Vienna

Efforts: 2 person x month

Contributors: Wang , visiting scientist, Kann

Documentation: available by Wang

The software for correcting bias in the ensemble system has been implemented, but haven’t tested due to the lack of historical data of the ensemble system.

  - Common EPS verification

Description and objectives: A common verification package is very necessary and useful for LAEF research and development. Works will be coordinated, proposal for the common verification package, like definitions of the common domain, data format, verification scores, verifying parameters, the truth (observation or analysis), and so on, will be made. Coordination/contribution from Data Manager (Kertesz) is expected.

Realization: Vienna, Budapest, Prague

Efforts: 3 person x month (1.5 LACE Funding)

Contributors: Kann, Hágel, Mladek, Wang, Kertesz

Documentation: stay report of Hágel and Mladek , LACE web

The common verification package has been developed for verifying the upper air parameters. The scores, like Talagrand diagram, Brier Score and skill score, ROC etc have been implemented. More details about the status of the common verification package can be found in the stay report of  Hágel and Mladek (LACE web)

  - Comparison between SRNWP-PEPS and ALADIN LAEF experiments

Description and objectives: To verifying the results of ALADIN LAEF, comparison will be made with the existing LAMEPS system SRNWP-PEPS. The purpose of this comparison is to better understand the multi-model EPS system.

Realization: Prague, Vienna

Efforts: 6 person x month (0.5 month LACE Funding)

Contributors: Mladek, Kann

Documentation: not available

Due to the data policy of SRNWP-PEPS, it is difficult to have the PEPS data for verification and comparison. This subject was not touched in 2006, and the funding was shifted to verification subject

  - Dynamical downscaling of ARPEGE EPS

Description and objectives: To investigating the performance, in particular the more added value of the downscaling of ARPEGE EPS. Cases, especially those related with big problem with precipitation forecast in ALADIN, will be investigated. Moreover, experiments with different optimisation time and target domain in ARPEGE EPS and then ALADIN downscaling are done.

Realization: Prague, Vienna, Budapest

Efforts: 6 person x month

Contributors: Mladek, Kann, Wang, Hágel, Horanyi

Documentation: the work in Pargue not available yet, the work in Vienna is partly in ALADIN newsletter 29, the work in Budapest is available from Horanyi and Hágel

The work in Budapest has been finished, and the result is written a paper. This is available by Horanyi and Hágel. A one-month test with dynamical downscaling of ARPEGE EPS, and the comparison with Breeding have been made, the result is shown in ALADIN newsletter.

- International collaboration / participation on projects related with LAMEPS

  - Participation and development of a Grand Limited-Area Model Ensemble Prediction System (GLAMEPS)

Description and objectives: At a mini-HIRLAM workshop on predictability in March 2006, a proposal has been made for development of a Grand Limited-Area Model Ensemble Prediction System (GLAMEPS) within ALADIN and HIRLAM partners, this idea is quite similar as ALADIN LAEF in LACE. ALADIN LAEF will take part in GLAMEPS as the LACE contribution and LACE will act as a single partner in this collaboration. Coordination and planning work on GLAMEPS with HIRLAM will be conducted.

Realization: Vienna

Estimated efforts: 0.5 person x month

Contributors: Wang, Klaric, Mladek, Tascu, Ivatek-Sahdan, Horanyi, Kann

Documentation: not available

In 2006, coordination and planning work on GLAMEPS were conducted by participation on GLAMEPS discussion during ALADIN Sofia workshop, and on the discussion and planning during ALADIN-HIRLAM workshop in Vienna.

  - Beijing 2008 Olympics Mesoscale Ensemble Prediction Research and Demonstration Project (B08RDP)

Description and objectives: Endorsed by WMO/WWRP, a five years research demonstration project (2005-2009) B08RDP has been originated for research and development of regional EPS  system. ZAMG/Meteo-France acting as a single partner, together with other participants, NCEP, NCAR, UKMO, MSC, JMA and CMA will run their LAMEPS in near real time for the period of Olympics 2008 over Beijing. Subjects, as scientific/technical coordination, computational environment, data exchange, telecommunication, regular exchange of research results (workshops), LAMEPS demonstration, common verification, inter-comparison, have been established and planned. For this project, ZAMG and Meteo-France have begun to develop the ALADIN LAEF since 2005.

Funding for implementation of ALADIN LAEF on B08RDP will be applied in May 2006.

Realization: Vienna, Toulouse

Efforts: 6 person x month

Contributors: Austrian & French Team: Wang, Bouttier, ......

Documentation: not available

Coordination and planning work together with other partners in the project were conducted in 2006. With the support of visiting scientists, some planning works on technical issues, like telecommunication, and verification etc have been done.

  - Mesoscale Alpine Programme Demonstration Phase (MAP D-Phase)

Description and objectives: MAP D-Phase is a forecast demonstration project supported by WMO/WWRP. One of the subjects of the project is to demonstrate the benefits in high impact weather forecasting over mountainous area from very high resolution NWP and the probabilistic forecast. Coordinated with another international project COPS (Convective and Orographically-induced Precipitation Study), June to August 2007 is chosen as the demonstration period. LACE  plans to provide the ALADIN LAEF forecast for MAP D-Phase,  if a suitable LAEF version is available before the demonstration period, otherwise ALADIN-AUSTRIA forecasts will be provided.

Realization: Vienna

Efforts: 0.5 person x month

Contributors: Wang, Kann

Documentation: not available

Participation on workshops and planning meetings.

- Other activities

An ALADIN-HIRLAM kick-off workshop on LAMEPS will be organized by LACE in Vienna at end of 2006 or beginning of 2007 (probably 9-10. Nov. 2006 ???). The exact date will be coordinated in ALADIN and HIRLAM. It is planned to invite the COSMO colleagues for the workshop too. Invitation for other experts on predictability from the projects B08RDP and MAP-D-Phase is also under consideration.

1st ALADIN-HIRLAM workshop on LAMEPS was held in Vienna from 13-14. Nov. 2006. Around 35 scientists from ALADIN, HIRLAM, COSMO and UKMO participated the workshop. Many issues related LAMEPS have been discussed, especially the project of GLAMEPS.

5.   WG Predictability Research and Development , fulfillment of  2006 / status and means

| ##### Subject 1. Uncertainty in initial conditions |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Action | Status | Person x months Realized/Planned | LACE Funds |
|  | Breeding | ###### ongoing | 3 / 6 months | no |
|  | ETKF | #### waiting | 3 months | no |
|  | ET | waiting | 3 months | no |
|  | SV | ###### ongoing | 5 months | no |
|  | Blending | ###### ongoing | 3 months | 1 month |

| ##### Subject 2: Uncertainty in lateral boundary conditions |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Action | Status | Person x months Realized/Planned | LACE Funds |
|  | NCEP perturbation | #### waiting | 3 months | No |

| ##### Subject 3: Uncertainty in model physics |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Action | Status | Person x months Realized/Planned | LACE funds |
|  | ALADIN multi-physics | #### ongoing | 2 months | no |
|  | Stochastic physics SKEB | #### waiting | 3 months | 1.5 months |

| ##### Subject 4: Downscaling, verification, post-processing, etc. |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Action | Status | Person x months Realized/Planned | LACE Funds |
|  | ECMWF downscaling | ongoing | 14.5 / 3 months | 2.0 month |
|  | Post-processing | waiting | 2 months | no |
|  | Common verification | ongoing | 3 months | 1.5 month |
|  | Comparison PEPS -- LAEF | ###### waiting | 6 months | 0.5 month |
|  | ARPEGE downscaling | ongoing | 6 / 0 months | No |

| ##### Subject 5: Participation on international research projects |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Action | Status | Person x months Realized/Planned | LACE Funds |
|  | GLAMEPS | #### ongoing | 0.5 month | no |
|  | B08RDP | #### waiting | 6 months | no |
|  | MAP D-Phase | waiting | 0.5 month | no |

| ##### Summary of means and LACE Funds |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  |  | Person x months Realized/Planned | LACE Funds |
|  | TOTAL |  | 54.5 / 49 months | 4.5 months |